## High Level Timeline
Date | Day | Goal
2017-05-12 | Friday | Receive Prompt
2017-05-13 | Saturday | Review bootstrap templates
2017-05-14 | Sunday | Planning Meeting at 7:30, Lisa's Place #3507 over a Manhattan
2017-05-15 | Monday | 1/2 Day Workshop in Class - Start Coding
2017-05-16 | Tuesday | Full Day Workshop in Class
2017-05-17 | Wednesday | Testing
2017-05-18 | Thursday | Testing
2017-05-19 | Friday | Presentation

## Detailed Plan
Date | Day | Goal | Notes
2017-05-12 | Friday | Receive Prompt | survey
2017-05-13 | Saturday | Review bootstrap templates | looked at 3 main ones, depends on MVP after we decide
2017-05-14 | Sunday | Planning Meeting at 7:30, Lisa's Place #3507 over a Manhattan
2017-05-15 | Monday | 1/2 Day Workshop in Class - Start Coding
2017-05-16 | Tuesday | Full Day Workshop in Class
2017-05-17 | Wednesday | Testing
2017-05-18 | Thursday | Testing
2017-05-19 | Friday | Presentation
step | task | subtask | day | date | owner | branch | status | notes
0 | set up templates |  | Sunday | 2017-05-15 | Tony |  | completed
1 | review bootstrap templates |  | Sunday | 2017-05-15 | all |  | completed | came up with a few: scroll, landing
2 | start user stories |  | Sunday | 2017-05-15 | all |  | completed
3 | meet at Lisa's 7:30-10 |  | Sunday | 2017-05-15 | all |  | completed
4 | npm install |  | Monday | 2017-05-15 | all |  | completed
5 | secret key |  | Monday | 2017-05-15 | all |  | completed
6 | set up branches |  | Monday | 2017-05-15 | all | development | completed
7 | spin up back end |  | Monday | 2017-05-15 |  |  | completed | nodemon
8 | spin up front end |  | Monday | 2017-05-15 |  |  | completed | grunt serve
9 | write ERD |  | Monday | 2017-05-15 | all |  | completed
10 | write wireframes |  | Monday | 2017-05-15 | all |  | in progress
11 | write user stories |  | Monday | 2017-05-15 | all |  | in progress
12 | set up issue for 1:1 with Chris |  | Monday | 2017-05-15 | Don |  | in progress
13 | update project plan |  | Monday | 2017-05-15 | Lisa |  | in progress
14 | curl requests client to api |  | Monday | 2017-05-15
15 |  | curl get all | Monday | 2017-05-15
16 |  | curl get one | Monday | 2017-05-15
17 |  | curl create | Monday | 2017-05-15
18 |  | curl destroy | Monday | 2017-05-15
19 |  | curl update | Monday | 2017-05-15
20 | add junk authentication forms in index.html |  | Monday | 2017-05-15 | Don | donsignin | completed
21 | update config file with back url |  | Monday | 2017-05-15 | one of us |  | completed
22 | review deployment guide? |  | Monday | 2017-05-15 | all |  | completed
23 | deploy front end |  | Monday | 2017-05-15 |  |  | completed
24 | deploy back end |  | Monday | 2017-05-15 | Lisa |  | completed | grunt build, grunt deploy from master branch
25 | decide MVP |  | Monday | 2017-05-15 | Tony |  | completed
26 | meeting tonight 6-8 @ Don's |  | Monday | 2017-05-15 |  |  | completed
27 | sign up api |  | Tuesday | 2017-05-16
28 | sign in api |  | Monday | 2017-05-15 | Don |  | completed | modifications | scripts/auth/api, events, js
29 | sign out api |  | Monday | 2017-05-15 | Don |  | completed | modifications
30 | change password api |  | Monday | 2017-05-15 | Don |  | completed | modifications
31 | sign up ui |  | Monday | 2017-05-15 | Don |  | completed | modifications
32 | sign in ui |  | Monday | 2017-05-15 | Don |  | completed | modifications
33 | sign out ui |  | Monday | 2017-05-15 | Don |  | completed | modifications
34 | change password ui |  | Monday | 2017-05-15 | Don |  | completed | modifications
35 | sign up events |  | Monday | 2017-05-15 | Don |  | completed | modifications
36 | sign in events |  | Monday | 2017-05-15 | Don |  | completed | modifications
37 | sign out events |  | Monday | 2017-05-15 | Don |  | completed | modifications
38 | change password events |  | Monday | 2017-05-15 | Don |  | completed | modifications
39 | test sign up from UI |  | Monday | 2017-05-15 | all |  | completed
40 | test sign in from UI |  | Monday | 2017-05-15 | all |  | completed
41 | test sign out from UI |  | Monday | 2017-05-15 | all |  | completed
42 | test change password from UI |  | Monday | 2017-05-15 | all |  | completed
43 | meet with Chris | take ERD, user stories, wireframes, plan | Tuesday | 2017-05-16 | all |  | completed
44 | finalize ERD |  | Tuesday | 2017-05-16 | all
45 | finalize user stories |  | Tuesday | 2017-05-16 | all
46 | finalize wireframe |  | Tuesday | 2017-05-16 | all
47 | upload ERD, user stories, wireframs |  | Tuesday | 2017-05-16 | all
48 | design schema |  | Tuesday | 2017-05-16 | all |  |  | data types, validations, editables, virtuals
49 | set up mongodb files |  | Tuesday | 2017-05-16 | all
50 |  | routes | Tuesday | 2017-05-16 | all
51 |  | controller surveys | Tuesday | 2017-05-16 | all |  |  | ref Users
52 |  | controller questions | Tuesday | 2017-05-16 | all
53 |  | model surveys (also schema) | Tuesday | 2017-05-16 | all |  |  | ref Users
54 |  | model questions (also schema) | Tuesday | 2017-05-16 | all |  |  | ref Surveys
55 | index - general |  | Tuesday | 2017-05-16
56 | stylesheet |  | Tuesday | 2017-05-16
57 | create seed file (optional) |  | Tuesday | 2017-05-15
58 | index - authentication |  | Tuesday | 2017-05-15
59 | index - other functionality |  | Tuesday | 2017-05-15
60 | animation |  | Tuesday | 2017-05-15
61 | create seed file (optional) |  | Tuesday | 2017-05-15
62 | index - authentication |  | Tuesday | 2017-05-16
63 | index - other functionality |  | Tuesday | 2017-05-16
64 | animation |  | Tuesday | 2017-05-16
65 | validate all connections b/w front/back |  | Tuesday | 2017-05-16
66 | polish index.html |  | Tuesday | 2017-05-16
67 | polish index.scss |  | Tuesday | 2017-05-16
68 | bug fixing |  | Tuesday | 2017-05-16
69 | bug fixing |  | Wednesday | 2017-05-17
70 | README for back-end |  | Wednesday | 2017-05-17
71 | README for front-end |  | Wednesday | 2017-05-17
72 | test authentication |  | Wednesday | 2017-05-17
73 | test CRUD from UI |  | Wednesday | 2017-05-17
74 | update UI to make it look pretty (optional) |  | Thursday | 2017-05-18
75 | ask friends/fam to test |  | Thursday | 2017-05-18
76 | presentation run-through |  | Friday | 2017-05-19

## Issues
Issue URL | Description | Status
https://git.generalassemb.ly/ga-wdi-boston/team-project/issues/274 | Product URL incorrect | Closed
https://git.generalassemb.ly/ga-wdi-boston/team-project/issues/266 | Request 1:1 | Open, artifacts attached

## User Stories
Authentication | blue = definitely
As a user, I want to sign up.
As a user, I want to sign in.
As a user, I want to sign out.
As a user, I want to change password.
As a user, I want to see all available surveys.
As a user, I want to see a dashboard.
As a user, I want to see responses to a survey .
Creator
As a creator, I want to create a survey.
As a creator, I want to add questions for my survey.
As a creator, I want to delete a survey.
As a creator, I want to have a scale from 1-5 for the survey questions (1=low, 5=high)
As a creator, I want takers to submit answers to my survey.
As a creator, I want to see the aggregated results of my survey.
As a creator, I want to see the average of all results per question of my survey. | maybe
As as creator, I want to preview the survey questions before submitting. | maybe
As a creator, I want to save my survey questions to database.
As a creator, I want to name my survey.
As a creator, I do not want to be able to answer questions to my survey. | maybe
As a creator, I want to update the name of my survey. | maybe
Creator questions
As a creator, I want to update my survey before any takers have answered my survey. | maybe
Takers
As a taker, I want to choose a survey from the list of all available surveys.
As a taker, I want to answer questions to a survey.
As a taker, I want to update my answers to a survey before submitting. | maybe
As a taker, I want to submit my survey answers.
As a taker, I cannot take a survey more than once. | maybe
Stretch
As a user, I want to configure my survey answer scale.
As a creator, I want to specify the number of questions in my survey before creating the questions.
As a taker, I want to see the results of other surveys.
As a user, I want to view all surveys that have been answered.
As a taker, I want to update my answers after submitting.
As a user, I want the dashboard to display total number of surveys.
As a user, I want the dashboard to display the number of surveys with answers.
As a creator, I want to update my survey after any takers have answered my survey.
As a creator, I want to delete questions for survey.
General Question
Do we allow non-authenticated users to view the survey names? | maybe
What is an active survey? | An active survey is a survey that exists in the database.
Do we need to CRUD everything?
Do we need to display the questions and individual scores?

## Requirements
Status | Deliverables
API built by the whole team hosted somewhere on the internet.
A client app that consumes your API built by the whole team hosted somewhere on the internet.
Git Repo for front-end with frequent commits from every teammember dating back to the very beginning of the project.
Git Repo for back-end with frequent commits from every teammember dating back to the very beginning of the project.
Technical Requirements
Use MongoDB and Express to build an API.
Create an API using at least 2 related models, one of which should be a user.
Include all major CRUD functions in a RESTful API for at least one non-user model.
Consume your own API by making a front-end with HTML, Javascript, and jQuery
Use authentication in your API to restrict access to appropriate users.
Craft thoughtful user stories together, as a team.
Manage team contributions and collaboration using a standard Git flow on Github.
Layout and style your front-end with clean and well-formatted CSS.
Deploy your application online so it's publicly accessible.
Not have any obvious user facing errors.

## Decisions
Date | Agreed/Pending | Decision | Group Project Guidelines
2017-05-10 | Agreed | 2 Standups / Day am and pm | From All I Really Need to Know I Learned in Kindergarten by Robert Fulghum:
2017-05-11 | Agreed | Planning Meeting on Sunday the 14th; think of some templates to discuss | Share everything.
2017-05-11 | Agreed | Repo on Sunday/Monday | Play fair.
2017-05-12 | Agreed | Merge twice a day, Noon and EOD. | Don't hit people.
2017-05-12 | agreed | All working on own branches, with name in label of branch | CLEAN UP YOUR OWN MESS.
2017-05-12 | Agreed | Will be working with Dev branch | Say you're SORRY when you HURT somebody.
2017-05-14 | Agreed | Deploying at minimum once per day. | TLDR; The Rules
You must not work alone.
You must not work quietly. Communication is very important for managing expectations.
Develop your plan together.
Identify dependencies between tasks so you know what to work on first.
Do not work on more than one task at a time.
You must record your decisions and share them with the group.
You must respect group decisions.
Everyone participates in code review before a merge.
Everyone must be present for merges. No one works on tasks while merge conflicts are being resolved.
Have regular standups.
Have regular retros.
But, Why?
Working in teams is an integral part of modern software development. There are considerable differences between working in a team on software and other group projects you may have worked on in the past. Though the group as a whole is responsible for making a product, each individual member is expected to contribute to the product by providing insight, quality assurance, and (of course) producing code. In software, there's always another task to complete, and it's tempting to work on many tasks at once. However, we're not just racing toward a finish line. Software is never complete.
In software teams, each member is valuable in part because of their unique experience and perspective. If the team is to succeed, knowledge gaps need to be filled. By sharing knowledge, we decrease what we call the "deltas" or differences in knowledge and specialties among team members. The best software teams are a mix of junior and senior members, the junior members providing what is called "beginner's mind" and senior members providing the technical know-how to solve difficult problems.
With these things in mind, here are some tips for ensuring each team member contributes in whatever capacity they can:
Always pair. This is crucial for decreasing deltas.
Pairs should work on one task at a time.
Ask questions of your pair if you are leading.
If you are following, interrupt your pair when you don't understand a decision.
If you are leading, answer your pair's questions with reasoned responses, not "gut feeling".
If either pair wants to experiment, entertain that desire even if you disagree, but time-box the experiment.
The group, being made up of individuals, is a collection of relationships. The group as a whole can be described in many of the same ways its members can: it is healthy or not, efficient or slow, happy or upset. As a collection of relationships, the group is either functional or dysfunctional. Here are some tips for maintaining group cohesion:
Have a stand-up meeting every morning. The purpose of this meeting is to review progress and set priorities for the day. Each member answers the following questions before discussing goals for the day as a group:
What did you work on yesterday?
What do you plan on working on today?
What is blocking you?
Can you help someone else who is blocked?
Have a retro at the end of each day. The purpose of this meeting is to share progress made to keep team members up-to-date. Retros are also valid places for sharing feelings, such as excitement, frustration, or overwhelm. A retro usually consists of "glow, grow, and shout outs".
"Glow" is something that went really well that day.
"Grow" is something you would like to see change.
"Shout outs" are public thanks to a team member who deserves recognition.
In addition to maintaining group cohesion and individual satisfaction, communicating regularly ensures transparency and ensures all voices are heard. You'll find it also helps avoid merge conflicts! Happy hacking.

## Standups
15 minutes, timed

## README Requirements
The README.md file inside your front-end repo should have:
A short description of your application.
A brief explanation of the technologies (Node modules, Express middleware etc) used.
A couple of paragraphs detailing the general approach you took.
Notes on any unsolved problems or major hurdles your team had to overcome.
Installation instructions for any dependencies.
A link to your user stories – who are your users, what do they want, and why?
A link to your ERD - what data models does your app use?
A link to your wireframes – sketches of major views / interfaces in your application.
A link to the deployed front-end app.
A link to the repo for your back-end.
The README.md file inside your back-end repo should have:
A short description of your application.
A catalog of routes (paths and methods) that the API expects.
A link to the deployed back-end app.
A link to the repo for your front-end.